## Sheet1
2015 Mitigation Action | Mitigation Type | Hazards Addressed | Status | Revised or New Mitigation Action | Likely Benefits | Likely Costs | Social | Technical | Administrative | Political | Legal | Economic | Environmental | Responsible Party | Cost & Funding | Timeframe
Culvert and bridge capacity improvements at the following locations:  Boston Post Road between Simeon Wilson & Thornton Ferry Road II  Stearns Road between Veterans Road and Route 122  Merrimack Road between Holt Road and Souhegan Ave | Structure and Infrastructure Projects | Riverine Flooding, Hurricane | Boston Post: No progress. Sterns Road: Raised the road and replaced the culvert. Merrimack: Added additional overflow pipe, replaced existing pipe | Flood mitigation improvements at Boston Post Road between Simeon Wilson & Thornton Ferry Road II including raising the road and studying potential culvert improvements | Boston Post Road will no longer flood and it will enable emergency responders and others to pass through the area during extreme rain events | DPW will provide a rough estimate
Establish mutual aid agreements with neighboring communities to address administering the NFIP following a major storm event. |  |  | No progress. Not a mitigation action, more on preparedness/response. Will not be tracked moving forward. | Deleted
Revise and enforce floodplain, stormwater, and erosion control regulations to improve floodplain management in Amherst. Utilize site plan regulations to encourage permeable driveways and surfaces to reduce runoff and promote groundwater recharge. |  |  | Stormwater Regulations have been updated. Permeable driveways and surfances are recommended but not required. Change to request an MS4 Coordinator to enable enforcement. | Completed
Reduce wildfire risk, including preventing or alleviating wildfires by proper separation of power lines as well as efficient response to fallen power lines; routinely inspecting the functionality of fire hydrants; and requiring and maintaining safe access for fire apparatus to wildland urban interface neighborhoods and properties. |  |  | Response to fallen powerlines is response action, recommend removal. Eversource has maintained public right of way vegetation with land owner permission. Problem is the trees on private property. Remove efficient response language. Change language to maintain awareness and notify land owners of dangerous trees. Item 2: Pennichuck has contract to maintain hydrants. Item 3: This is being currently dealt with in site plan reviews. | Item 1 (response to fallen power lines) is removed as it's a response action. Item 2 is removed and will be moved to mitigation capabilities as it's an ongoing effort. Item 3 is removed and will be moved to mitigation capabilities as it's an ongoing effort as part of site plan reviews.
Conduct outreach and education programs to increase awareness of wildfire, tornado, hurricane, extreme temperatures, and carbon monoxide risks. Utilize Code Red and community access TV. | Education and Awareness Programs | All Hazards | Has not been utilized related to mitigation. Carbon Monoxide awareness has been promoted. Add mitigation related content to DPW Social Media. Amherst Fire has been promoting wildfire mitigation. | Conduct five natural hazard mitigation outreach and education activities to increase awareness of natural hazard risks and ways homeowners and businesses can mitigate them. | Help the public to take mitigation actions on their own without government intervention. Reduced losses for homeowners and businesses after disasters | Primarily labor costs, and time. $5,000
Monitor water supply and drought conditions. Utilize NH Division of Forest and Lands reports to monitor drought indicators. | Local Plans and Regulations | Drought | Recommend revision to something more mitigation related. Amherst does monitor this regularly. | Identify local drought indicators, such as precipitation, temperature, surface water levels, soil moisture, etc and develop criteria or triggers for drought-related actions | Preserves aquifer and water supply prior to a crisis situation. Will also ensure fire protection is not degraded due to water loss. | Time is primary cost. Also could be a consultant or engineering firm. $10,000 to $100,000
Proactively enforce the International Building Code (IBC) and International Residential Code (IRC) to protect buildings and infrastructure from the impacts of severe winter weather, hurricanes, flooding, and earthquake. | Local Plans and Regulations | Earthquake, Hail, Hurricane, Riverine Flooding, Strong Wind, Tornado, Wildfire, Winter Weather | This has been enforced over the last 5. The state did update this within the last 5 years. Advocate for a more up to date edition of the code with the State. | Prepare and train local code enforcement staff on the natural hazard mitigation components of the 2024 International Code Council suite of state-adopted building codes upon passage of proposed state legislation to follow a "one cycle old" adoption process | More aware of how the new codes reduce risk in the community. Would increase safety and viability of structures. May be a reduction of costs due to new efficient technologies and processes. Reduced energy costs and fuel consumption. | $1200 per year including training classes and due to NHBOA. ICC membership. Time for staff as well. Potentially a cost involved with the builders perspective.
Protect critical facilities and infrastructure from lightning damage. Install and maintain surge protection on critical electronic equipment and grounding on radio towers. Protect power lines by working with utility companies to harden electrical infrastructure, including trimming trees near power lines. Consider the costs and benefits of requiring that overhead power lines be buried in all new developments. | Structure and Infrastructure Projects | Lightning | Item 1: Probably no progress on additional surge protectors and lightning protection. Item 2: Eversource has done electronic monitoring on their systems with SCADA. In areas without SCADA, they have installed trip saver fusing. Hardened the poles out of the Amherest substation. Item 3: Eversource is trimming right of ways to easment specification. Installed steel structures instead of wooden poles in right of ways. Item 4: Buried powerlines are not a requirement but most are doing it. | Conduct an assessment of all critical electronic systems within municipal property to identify lightning protection levels and possible mitigation strategies | Would become aware of what systems are vulnerable to lightning strikes. Would then be able to develop a cost effective implementation plan. | Consultant to come in and review this. $10,000-$50,000
Protect critical facilities and infrastructure from lightning damage. Install and maintain surge protection on critical electronic equipment and grounding on radio towers. Protect power lines by working with utility companies to harden electrical infrastructure, including trimming trees near power lines. Consider the costs and benefits of requiring that overhead power lines be buried in all new developments. | Structure and Infrastructure Projects | Hurricane, Ice Storm, Strong Wind, Tornado, Winter Weather, Lightning | Item 1: Probably no progress on additional surge protectors and lightning protection. Item 2: Eversource has done electronic monitoring on their systems with SCADA. In areas without SCADA, they have installed trip saver fusing. Hardened the poles out of the Amherest substation. Item 3: Eversource is trimming right of ways to easment specification. Installed steel structures instead of wooden poles in right of ways. Item 4: Buried powerlines are not a requirement but most are doing it. | Assess electric distribution system in Amherst and prioritize locations to replace open wire to covered wire | If limbs fall on the wires, it likely will not cause an outage as quickly. Properly installed, reduces lightning hazard. | If not caught in a timely manner, it can burn the wire down. More challenges with splicing wires. Covered wires that fall down during a storm may still be live creating a public safety hazard. $5-10 million for critical lines
Protect critical facilities and infrastructure from lightning damage. Install and maintain surge protection on critical electronic equipment and grounding on radio towers. Protect power lines by working with utility companies to harden electrical infrastructure, including trimming trees near power lines. Consider the costs and benefits of requiring that overhead power lines be buried in all new developments. | Structure and Infrastructure Projects | Hurricane, Ice Storm, Strong Wind, Tornado, Winter Weather | Item 1: Probably no progress on additional surge protectors and lightning protection. Item 2: Eversource has done electronic monitoring on their systems with SCADA. In areas without SCADA, they have installed trip saver fusing. Hardened the poles out of the Amherest substation. Item 3: Eversource is trimming right of ways to easment specification. Installed steel structures instead of wooden poles in right of ways. Item 4: Buried powerlines are not a requirement but most are doing it. This should be removed | Collaboratively identify areas with dangerous trees and conduct outreach with property owners on strategies for removal or trimming | The removal of more tree hazards that would reduce outage impacts. | Time for tree warden and conservation commission to assess tree problem areas. $1500 for the time of the tree warden.
Protect vulnerable populations from the impacts of extreme temperatures and severe winter storms by establishing shelters and cooling stations at designated municipal and school facilities. |  |  | Recommend Removal. Amherst has used the fire station as a warming center during long term power outage. Most people don't want to leave. | Deleted
Improve stormwater drainage system capacity and flood control infrastructure. Consider costs and benefits of a variety of infrastructure upgrades, including stormwater pipe storage, stormwater ponds, stormwater tank storage, and culvert upsizing and realignment. |  |  | There has been some culvert upsizing done and adding secondary culverts for overflow protection. There have been some stormwater tanks in private development in the last five years. This is an ongoing action that is being done through existing stormwater regs and site review. | Remove and shift to mitigation capabilities as part of site plan review as this is ongoing
Work with property owners to elevate or remove loss structures from flood-prone areas to minimize future flood losses. | Structure and Infastructure Projects | Riverine Flooding, Hurricane | Nothing has been done on this action | Conduct a community-wide assessment to identify properties with structures that could be elevated or removed from flood areas to minimize future losses. | Now be aware of locations where mitigation actions can be taken with a prioritized implementation plan. | Time for town staff. $50k-100k for consultant
Map and assess vulnerability to erosion. Conduct stream assessments and prepare fluvial erosion hazard zone maps. | Local Plans and Regulations | Riverine Flooding, Hurricane | No additional mapping that has been done. Hire a GIS person to assist with these types of assessments. | Hire a GIS Coordinator to map and assess flood and erosion concerns. | Now a person on staff that can assist with mapping during mitigation projects. Reduce workload in Community Development. Reduce DPW costs, particularly around MS4. | Position would likely be 100k including benefits per year
| Local Plans and Regulations | Riverine Flooding, Hurricane | New | Investigate possible actions to enforce driveway regulations at 82 Broadway to prevent gravel washouts during extreme rain events | Develop an action plan with potential strategies to resolve the issue. Reduce liability on the towns part by having official legal review and opinion on who is responsible for fixing the problem. | Time of staff $5000 including legal counsel
| Local Plans and Regulations | Riverine Flooding, Hurricane | New | Hire a Coordinator to manage the Municipal Separate Stormwater Sewer Systems (MS4) program for the town. Position would have special emphasis on promoting stormwater hazard mitigation activities across the community. | Now a person on staff that can assist with managing stormwater program. Reduce workload in Community Development. Reduce DPW costs, particularly around MS4. | 100k total including benefits
| Education and Awareness | Cold Wave | New | Conduct an education campaign for homeowners and builders on how to protect their pipes, including locating water pipes on the inside of building insulation or keeping them out of attics, crawl spaces, and vulnerable outside walls. | Residents and businesses would be more aware of mitigation techniques to reduce losses. Less calls for fire department for frozen pipes. Less insurance costs for homeowners. | $1500 for time of staff and flyers pamphlets
| Local Plans and Regulations | Severe Winter Weather, Cold Wave | New | Create a plan and training for treatments and other innovative practices to maintain satisfactory road and debris clearing capabilities during extreme cold events. | Realistic plan that can be used during extreme cold events. Safer roadways during extreme cold | $2500 to develop the plan and allow staff to attend the training. Treatments would likely be more environmentally friendly and more efficient and cost effective.
| Local Plans and Regulations | Heat Wave | New | Work with the Planning Board to develop extreme heat mitigating vegetation options to incorporate into site plan review | More trees planted in more densely develoeped areas. More shade during high heat events. | Time to develop the guidance $1500
| Local Plans and Regulations | Landslide | New | Use GIS to identify and map landslide hazard areas | Identify the areas that should be prioritized for future mitigation actions on the landslide hazard. | 10-25k for consultant to complete an assessment